## April 1
|  |  | Weekly Sprint Sheet |  | Team Members | Email
Project: Running Ducks |  |  |  |  | Angela Cuevas | acueva6@uic.edu
Week Of: 4/22 |  |  |  |  | Aswin Manoj | amanoj3@uic.edu
[5 empty] | Zeke Thornburgh | ethorn3@uic.edu
Action Item | Item ID | Team Member | Last Week | This Week | Next Week | Issues
Maze Logic | ML0 | Angela Cuevas |  | Maze is created and clues disbursed | Link duck's movements to changes in maze
Duck Logic | DL0 | Aswin Manoj |  | Work on the logic for duck's movements | Create necessary GUI elements
Team Logic | TL0 | Zeke Thornburgh |  | Clues/directions displayed | Connect choices with duck
Github | DC0 | Zeke Thornburgh | Repo Setup | Merge NetworkBasics with master
Documentation | DC1 | Aswin Manoj |  | Description of project
Networking | NW0 | Zeke Thornburgh |  | Network Basics | Controls over networking(Similar to TL0)